## Sheet1
Date received | Subject/service | Request | Contact name | Contact details | Anticipated time requirement | Priority | Deadline | Status | Comments
| Medical Education |  | Abigail James |  | 0.25 days | 2 | 2020-08-21 | Complete
| Video consultation | Waiting rooms formatting overhaul | Mark Cahalane |  | 0.5 days | 5 | 2020-08-21 | Complete
| Recovery College | New webpages | David Williams |  | 0.5 days |  | 2020-08-21 | complete
| Major Trauma Centre |  | Ceri |  |  | 5
| Children, Young People and Family Health Services | Final Feedback from Holly | Holly Tarren | 07976 787588
| WOD | Pay Progesson Toolkit / VBA Toolkit | Rachel Pressley
| Pharmacy - Presribing Service |  | Tracy Mends | 002921 836144 |  |  |  | Complete | Awaiting further info from Tracy re updates on Community Pharmacy
| Diabetes | Meeting on 22nd/Sept | Louise/Helen Griffiths/ Jon Baldwin |  |  |  |  | Ongoing | Completed first section - ongoing - Sent email thread to Lousie for attentin Helen Griffiths
| Workforce Governance - Band 5 Nurses | [6 empty] | Complete
| CAV 24/7 | Create pages for the new service | [5 empty] | Complete
| Welsh Language | Establish Welsh versions of pages | [5 empty] | Complete
| Young Volunteer Programme |  | Kelly Marlow |  |  |  |  | Ongoing | Awaiting copy and feedback
| Directory of Services plugin | Update from Cascade content | [5 empty] | Complete
| Patient Safety | Establish new section of website - Patient Safety Forms linked | Ann Jones | Ann.Jones11@wales.nhs.uk |  |  |  | Not started | Content drip feeding through from Ann
| Department of Sexual Health | Page updates - emailed Lydia - awaiting response | Lydia Harrison | 07811 423819 |  |  |  |  | Awaiting copy and feedback
| Forms | Need uploading to MURA - linking | Helen |  |  |  |  | Not started | need uploading to Mura
| Flu Campaign |  | Louise |  |  |  |  | Complete
| Noah's Ark | Updates to Children's Hospital pages - tiles /typeface/logos | Jayne |  |  |  |  | Ongoing
| Continuing Healthcare | [6 empty] | Complete
| Commissioning Team | Links to files - Individual Funding requests | Gemma Farley Holmond |  |  |  |  | Ongoing
| 3 Ways | Hyperlinks | Jenna |  |  |  |  | Ongoing
| Integrated Autism Services | Updated the pages - awaiting Feedback from Kevin/Manager
| Links to all the Publications Section |  | Helen Bricknell |  |  |  |  | Ongoing
| Community Pharmacy | 2 Uploads completed - wants a meeting about sub pages | Tracy Mendes |  |  |  |  | Ongoing
| Cardiothoracic Dept | New webpages - meeting 28th Sept | Juliet Launchbury |  |  |  |  | Ongoing | Had initial meeting - awaiting content
| Accessiblity Statement | Ongoing | Luke |  |  |  |  | Ongoing
| Podiatry Website | Updates to Podiatry Section | Steve Coombes/Mathew King | 02920 335242
| Staff Benefits | PDF uploads | Jane Catherall
| Stroke Clinic | Awaiting | Pedro Duarte | [5 empty] | No confirmation from Pedro
| Annual General Meeting Documents |  | Helen Griffiths |  |  |  |  | Completed
| South and East Localities | Continuing Healthcare Updates | Callum Mewett | 02920 335 509 |  |  |  | Completed
| NHS 111 Wales changes |  | Ceri
| Citizens Report / Safety Plan/Morbidiy |  | Bryn/Luke |  |  |  |  | Completed
| FAQ Accordian - New Hospital Wing |  | Jenna |  |  |  |  | Completed
| News article - Smoking reduction in Wales |  | Louise |  |  |  |  | Complete
| Research and Development | New material for R and D | Graham Law | 07793 914751 |  |  |  | Ongoing | Awaiting new material
| Nephrology and Transplant Analysis | Dialysis materal uploaded | Amanda Davies
| Advocacy - PDF QR Codes |  | Abigail Harris |  |  |  |  | Completed
| Compliments Concerns and Complaints | Compliments from Patients | Laura |  |  |  |  | Complete
| Clinical Coding | Awaiting updates from manager | Dan Jones |  |  |  |  | Complete
| Visitor Information - COVID 19 information | Updates to pages | Ceri |  |  |  |  | Complete
| Annual reports uploaded/Minutes | Update new information | Ceri/Helen Bricknell |  |  |  |  | Complete
| Recovery College - News Article | News Article | David |  |  |  |  | Complete
| OH Physio therapy | Received New Material | Carol Falcon/Muark Dunford | 02920 743264 |  |  |  | Ongoing
| Time for change news article | News Article | Nimyrah |  |  |  |  | Complete
| Patient Experience | Changes to original web content | Sarah Davies | 7973715912 |  |  |  | Ongoing
| Honorary Contracts | Changes to copy/pdf's | Rachel Pressley |  |  |  |  | Completed
| Employee Wellbeing Service | Eventbrite Event Changes - Virtual | Abigail McCullum |  |  |  |  | Completed
| CYPF Name change news article | News articl;e | Jayne |  |  |  |  | Completed
| New Dementia Website | News Article | Louise |  |  |  |  | Completed
| LPF Updates - WOD | LPF Update | Rachel Pressley |  |  |  |  | Completed
| UHB Maternity Award | News Article | Jayne
| Job Description Library | Page updaes | Carol Falcon |  |  |  |  | Completed
| Community Pharmacy 0 | PDF update | Louis Yau |  |  |  |  | Completed
| Orthopaedic OH | New page/ video - awaiting material | Bev Pretty |  |  |  |  | Ongoing
| CAV WCP - Mobile App Comms |  | Bill Mclenon |  |  |  |  | Ongoing
| Queens Birthday Honours | News article | Jayne |  |  |  |  | Completed
| Maternity Website | Updates - awaiting material | Maryanne Bray |  |  |  |  | Ongoing
| Black History Month | News article | Nimyrah |  |  |  |  | Completed
| Barry Hospital | Newsletter | Simon |  |  |  |  | Completed
| PHW | Booklet | Suzanne Wood |  |  |  |  | Awaiting
| Medical Workforce | Web page updates | Richard Mansell |  |  |  |  | Completed
| Video upload to CAVUHB Youtube | Video link | Raj Khan |  |  |  |  | Completed
| WOD Updates | Changes to pages | Carol Falcon |  |  |  |  | Completed
| Flu Vaccination Clinic | News article | Louis Yau |  |  |  |  | Completed
| All Wales Diabetic Patients Research Group | Diabetic Newsletter | Louis Yau |  |  |  |  | Completed
| All Wales Diabetic Patients Research Group News | News article | Jayne |  |  |  |  | Completed
| Clinical Coding | Privacy Notice Updates | Daniel Jones |  |  |  |  | Completed
| CYPF | Face to Face Appointments | Holy Tarren |  |  |  |  | Completed
| Primary Care South and East Localities | Page updates | Calum Mewett |  |  |  |  | Completed
| CAV 24/70 | Web page updates | Ceri |  |  |  |  | Completed
| Shumae Day | News Article | Nimyrah |  |  |  |  | Completed
| WOD Toolkits - Retire and Return | Page updates | Carol Falcon |  |  |  |  | Completed
| Teddy Bear Nurseries | Page updates | Rachel Pressley |  |  |  |  | Completed
| Beat Flu Campaign | News Article | Louis Yau |  |  |  |  | Completed
| Recovery College | News Article | David |  |  |  |  | Completed
| Rehabilitation Unit |  | Lewis Crown | 02920 313931